Project Proposal

Pharmacy Management System – Desktop Application

Prepared by: Faiz Hashmi – Senior Software Engineer

Date: 17 October 2026

Version: 1.0  |  Quotation valid for 30 days

1. Introduction

This proposal presents a milestone-based plan to design, develop, install and hand over a desktop Pharmacy Management System for a single pharmacy run by a doctor. The client referenced the D Watson pharmacy system; the scope below covers the parts of that kind of system that a single pharmacy uses every day. Two options are quoted separately:

• Option 1 – Purchasing & Stock Management: suppliers, purchases, batch/expiry stock, stock removal and expiry/low-stock alarms.

• Option 2 – Purchasing + Sales & Billing: everything in Option 1, plus a counter sales (POS) screen, printed bills and sales history.

Every optional add-on is priced individually in Section 6, so the client can start small and add features later.

2. Project Scope

2.1 Option 1 – Purchasing & Stock Management

Note: Anything not listed under "Included" is not part of Option 1.

Included Modules – Option 1:

1. Setup & Access

Flow 1: First-run setup (pharmacy name, address, licence no., logo for printouts)

Flow 2: Owner login with password, and password change

Flow 3: Basic manual backup to a folder / USB drive and restore

2. Medicine Catalogue

Flow 1: Add / edit / deactivate a medicine (brand name, generic/salt formula, strength, form, company, category)

Flow 2: Search medicines by brand name or by generic/salt (shows substitutes with the same formula)

Flow 3: Set a minimum stock level and an expiry warning period per medicine (or use the global default)

3. Company & Supplier Records

Flow 1: Add / edit medicine companies (manufacturers)

Flow 2: Add / edit suppliers / distributors (contact person, phone, address, NTN if any)

Flow 3: View the purchase history of a supplier

4. Purchases & Stock-In

Flow 1: Record a purchase: supplier, supplier invoice no., invoice date, received date

Flow 2: Add purchase lines: medicine, batch no., expiry date, quantity, bonus quantity, purchase price, MRP / sale price

Flow 3: Save the purchase, which adds the stock to the matching batches automatically

Flow 4: View, search and reprint (A4) a recorded purchase; edit it with the change logged

5. Stock View & Search

Flow 1: Current stock balance per medicine (total of all batches)

Flow 2: Batch details: batch no., expiry, quantity left, purchase price, supplier

Flow 3: Filter stock by company, category, supplier, expiry range or low stock

6. Stock-Out & Adjustments (how stock is reduced without a sales module)

Flow 1: Stock Issue: record medicine used / dispensed (e.g. in the clinic), batch picked earliest-expiry-first

Flow 2: Write-off: record damaged, expired or missing stock with a reason

Flow 3: Physical stock count: enter the counted quantity, and the system posts the difference as an adjustment

Flow 4: Stock movement history (ledger) per medicine and batch, showing every in, out and adjustment

7. Expiry & Low-Stock Alarms

Flow 1: Dashboard tiles: Expired, Expiring Soon, Low Stock, Out of Stock

Flow 2: Flashing red/amber highlights on affected medicines across stock screens

Flow 3: Sound alarm on app start and once per day while alerts are open (can be muted or snoozed). Sound alarm is included.

Flow 4: Settings: global expiry warning period (default 6 months, to be confirmed with the client) and default minimum stock level

Excluded Modules – Option 1:

1. Sales & Billing  =>  "Included in Option 2"

2. Every item in Section 6 (Optional Add-ons)  =>  "Priced separately"

2.2 Option 2 – Purchasing + Sales & Billing

Note: Includes every module in Option 1 plus the modules below.

Included Modules – Option 2 (in addition to Option 1):

8. Counter Sale (POS)

Flow 1: Search and add medicines to the bill by brand name or by generic/salt

Flow 2: Enter quantity; the sale price is pre-filled and can be edited by the owner

Flow 3: Automatic bill total, cash received and change returned

Flow 4: Expired batches are blocked from sale; a warning shows when stock is insufficient

9. Batch Deduction

Flow 1: Sold quantity is deducted from the earliest-expiring batch first (FEFO), splitting across batches when needed

Flow 2: Stock alarms update immediately after each sale

10. Bills & Receipts

Flow 1: Print a bill on an 80 mm thermal receipt printer or on A4

Flow 2: Save every bill with a sequential bill number

Flow 3: Search and reprint any past bill

Flow 4: Cancel (void) a bill by the owner, which restores the stock and logs the reason

11. Sales History & Daily Totals

Flow 1: Sales history with filters (date range, bill no., medicine)

Flow 2: Daily sales total and number of bills; day-end summary print

Excluded Modules – Option 2:

1. Discounts, taxes, customer credit, returns, staff logins  =>  "Optional add-ons (Section 6)"

2. FBR POS / e-invoicing integration  =>  "Optional add-on (Section 6)"

3. Technology Stack & Platform

• Application: Flutter Desktop, a native Windows app (.exe installer)

• Database: SQLite (local, encrypted at rest), stored on the pharmacy computer

• Supported OS: Windows 10 and Windows 11 (64-bit). macOS can be built on request.

• Offline: Yes. The system works fully offline; internet is needed only for the remote/cloud add-ons.

• Printing: 80 mm thermal receipt printers (ESC/POS) and any Windows A4 printer

• Minimum PC: Intel Core i3 / 4 GB RAM / 10 GB free disk, 1366×768 screen

• Language: English interface (Urdu printouts can be quoted on request)

4. Project Timeline

4.1 Option 1 – 6 Weeks

| Modules | Wks | Design Screens | Desktop Dev | Database / Logic |
| --- | --- | --- | --- | --- |
| Foundation & Setup | 1 | • App shell & design system • Setup wizard & login • Dashboard layout | • Windows app skeleton • Navigation & theming • Installer project | • SQLite schema & migrations • Encryption • Backup / restore |
| Catalogue & Suppliers | 2 | • Medicine form & list • Company / supplier screens | • CRUD screens • Salt/generic search | • Medicine, company, supplier tables • Search index |
| Purchases & Stock-In | 3-4 | • Purchase entry grid • Purchase list & detail • Stock & batch views | • Keyboard-first purchase entry • A4 purchase print | • Batch / expiry model • Stock ledger • Edit logging |
| Stock-Out & Alarms | 5 | • Stock issue / write-off • Physical count • Alert tiles & highlights | • Flashing indicators • Sound alarm, snooze & mute | • FEFO batch picking • Alert rules & thresholds |
| UAT & Handover | 6 | • Design QA | • Bug fixes • Release build | • Testing with the client's real data • Installation & training |

4.2 Option 2 – 9 Weeks

Weeks 1–5 are the same as Option 1, then:

| Modules | Wks | Design Screens | Desktop Dev | Database / Logic |
| --- | --- | --- | --- | --- |
| Counter Sale (POS) | 6-7 | • POS screen • Bill preview | • Fast keyboard / mouse billing • Insufficient-stock & expired-batch guards | • Sales model • FEFO deduction across batches |
| Bills & Sales History | 8 | • Thermal & A4 bill layouts • Sales history & day-end | • Printing & reprint • Void bill | • Bill numbering • Daily totals |
| UAT & Handover | 9 | • Design QA | • Bug fixes • Release build | • Testing with real data • Installation, printer setup & training |

5. Project Payment Schedule

All prices are in USD, are one-time, and exclude applicable taxes (if any). There is no recurring licence fee for the core system. PKR payment can be agreed at the exchange rate on the invoice date.

5.1 Option 1 – Total: USD 2,000  |  Delivery: 6 weeks

| Milestone | Duration | Price Quote | Modules Covered | Acceptance |
| --- | --- | --- | --- | --- |
| Advance (15%) | On signing | USD 300 | Requirement sign-off, data sample, setup | Signed scope |
| Milestone 1 | Weeks 1–2 | USD 500 | Foundation & Setup, Catalogue & Suppliers | Demo build approved |
| Milestone 2 | Weeks 3–4 | USD 600 | Purchases & Stock-In, Stock View | Demo build approved |
| Milestone 3 | Weeks 5–6 | USD 600 | Stock-Out & Alarms, UAT, installation, training | Installed at pharmacy |
| Total | 6 weeks | USD 2,000 |  |  |

Calculation: $300 (advance) + $500 (M1) + $600 (M2) + $600 (M3) = USD 2,000

5.2 Option 2 – Total: USD 3,200  |  Delivery: 9 weeks

Extra cost to add Sales & Billing to Option 1: USD 1,200 (+3 weeks)

| Milestone | Duration | Price Quote | Modules Covered | Acceptance |
| --- | --- | --- | --- | --- |
| Advance (15%) | On signing | USD 480 | Requirement sign-off, data sample, setup | Signed scope |
| Milestone 1 | Weeks 1–2 | USD 500 | Foundation & Setup, Catalogue & Suppliers | Demo build approved |
| Milestone 2 | Weeks 3–4 | USD 600 | Purchases & Stock-In, Stock View | Demo build approved |
| Milestone 3 | Week 5 | USD 450 | Stock-Out & Alarms | Demo build approved |
| Milestone 4 | Weeks 6–7 | USD 700 | Counter Sale (POS), batch deduction | Demo build approved |
| Milestone 5 | Weeks 8–9 | USD 470 | Bills & Sales History, UAT, installation, printer setup, training | Installed at pharmacy |
| Total | 9 weeks | USD 3,200 |  |  |

Calculation: $480 (advance) + $500 (M1) + $600 (M2) + $450 (M3) + $700 (M4) + $470 (M5) = USD 3,200

Advance Payment

• Advance Payment: 15% of the selected option is paid upfront.

• Purpose: Covers requirement sign-off, database design and project setup.

• Cancellation: If the client decides not to proceed, the advance is retained for the preparatory work done.

• Milestone payments: Each milestone is invoiced when its demo build is approved. The next milestone starts after payment.

• Change requests: Features outside this scope are quoted separately before work starts.

6. Optional Add-ons (Priced Separately)

These are optional and not confirmed. Each add-on is a one-time price added to the milestone in which it is delivered. "Needs Option 2" means the add-on depends on the Sales & Billing module.

| Add-on | What it includes | Extra cost | Time | Needs Option 2? |
| --- | --- | --- | --- | --- |
| Supplier accounts | Payments to suppliers, outstanding balances, supplier statement (print / PDF) | USD 350 | +1 wk | No |
| Returns & stock corrections | Supplier returns linked to purchase/batch; customer returns against a bill. (Damaged/missing write-offs are included in Option 1.) | USD 300 | +1 wk | Customer returns only |
| Barcode scanning | USB/Bluetooth scanner for stock entry and sales; map one or more barcodes per medicine | USD 200 | +0.5 wk | Sales scanning only |
| Barcode label printing | Design and print shelf/medicine labels (name, price, batch, expiry, barcode) | USD 250 | +0.5 wk | No (needs label printer) |
| Pack & unit selling | Box → strip → tablet conversion; buy in boxes, sell in strips or tablets with correct stock | USD 400 | +1 wk | Unit selling only |
| User accounts | Separate staff logins, role permissions (Owner / Salesperson / Store), audit log of changes | USD 350 | +1 wk | No |
| Backup & restore (automatic) | Scheduled automatic backups to a second drive/USB, retention, one-click restore | USD 200 | +0.5 wk | No |
| Reports & exports | Stock value, purchases, near-expiry, dead stock, sales and profit reports; Excel & PDF export | USD 450 | +1 wk | Sales & profit reports only |
| Import existing records | Excel template, validation and import of medicines, opening stock and batches | USD 200 | +0.5 wk | No |
| Customer accounts | Customer records, credit sales, payments received, outstanding balances | USD 350 | +1 wk | Yes |
| Discounts & taxes | Item and bill discounts, configurable tax rates on bills | USD 250 | +0.5 wk | Yes |
| Prescription printing | Doctor's prescription entry with patient name/age, medicine, dose, duration; print on letterhead | USD 300 | +1 wk | No (send-to-bill needs Option 2) |
| Multiple computers (LAN) | One computer acts as the server, others connect over the local network with shared records | USD 700 | +1.5 wks | No |
| Multiple branches | Separate stock per branch, branch transfers, consolidated view | USD 1,200 | +3 wks | No (needs Remote/cloud) |
| Remote / cloud access | Cloud database and sync; owner can view stock and sales remotely | USD 1,400 | +3 wks | No |

6.1 Other Suggested Add-ons

| Add-on | What it includes | Extra cost | Time | Needs Option 2? |
| --- | --- | --- | --- | --- |
| Controlled drugs register | Separate register for narcotic / psychotropic medicines with prescription reference, as required by drug inspectors | USD 250 | +0.5 wk | No |
| Reorder suggestions | Suggested purchase list from low stock and recent usage; print / send to supplier | USD 250 | +0.5 wk | No |
| Owner dashboard | Charts for sales, stock value, expiring value and top medicines | USD 200 | +0.5 wk | Sales charts only |
| FBR POS integration | Report each bill to FBR and print the FBR invoice number / QR on the bill (if the pharmacy is required to integrate) | USD 600 | +1.5 wks | Yes (and Discounts & taxes) |

Note: Multiple computers, Multiple branches, Remote/cloud access and Pack & unit selling change the database design. They should be decided before Milestone 1. Adding them after delivery may cost more than the prices above.

7. Deliverables

• Windows installer (.exe) of the Pharmacy Management System for the selected option and add-ons

• Installation on the pharmacy computer (on-site in the same city or remote via AnyDesk)

• Printer setup: receipt printer and A4 printer (and label printer / scanner if those add-ons are taken)

• Training: one session (up to 2 hours) for the owner and staff, plus a short user guide (PDF)

• Complete source code and database schema handed over after the final payment

8. Ownership, Warranty & Support

• Source code ownership: The client owns the source code and data after the final payment.

• Bug fixes: Free bug fixes for 60 days after go-live for anything that does not work as described in this proposal.

• Support after warranty (optional): USD 30 / month or USD 300 / year for bug fixes, remote help and minor changes (up to 4 hours / month).

• New features after delivery: Quoted separately.

9. Client's Support

To ensure timely delivery, the following is expected from the client:

Information & Data:

• Pharmacy name, address, licence no. and logo for printouts

• A sample of the current medicine list, suppliers and a few purchase invoices

• Confirmation of the expiry warning period (e.g. 6 months) and default minimum stock level

• One contact person who can test and approve each milestone within 3 working days

Hardware & Licences:

• A Windows 10/11 computer with a valid Windows licence

• Printers and scanners as required (see Appendix A); purchased by the client

• For Remote/cloud add-ons: an internet connection and a cloud hosting account

Appendix A – One-time & Recurring Costs (Third-Party)

These are not part of the development price. Prices are indicative and depend on brand and market.

| Item | Needed for | Type | Indicative cost |
| --- | --- | --- | --- |
| 80 mm thermal receipt printer | Option 2 bills | One-time | PKR 12,000 – 25,000 |
| USB barcode scanner | Barcode scanning add-on | One-time | PKR 4,000 – 12,000 |
| Barcode label printer + label rolls | Label printing add-on | One-time + consumables | PKR 25,000 – 50,000 |
| USB drive / external disk | Backups | One-time | PKR 3,000 – 10,000 |
| UPS for pharmacy PC | Recommended (protects data during load-shedding) | One-time | PKR 15,000 – 40,000 |
| Cloud server / database | Remote/cloud & Multiple branches add-ons | Recurring | USD 10 – 25 / month |
| Core system licence | Option 1 / Option 2 | — | None (no recurring fee) |

Appendix B – Answers to Quotation Questions

| Question | Answer |
| --- | --- |
| Currency | USD (PKR at the invoice-date rate on request) |
| One-time vs recurring cost | Development is one-time. No recurring cost unless Remote/cloud add-ons or paid support are taken. |
| Supported desktop OS | Windows 10 / 11 (64-bit) |
| Works offline? | Yes, fully offline |
| Sound alarm included? | Yes, with flashing highlights, mute and snooze |
| Stock reduction without sales (Option 1) | Stock Issue, Write-off and Physical Count screens (Section 2.1, Module 6) |
| Installation / printer setup / training | Included (Section 7) |
| Source code ownership | Client, after final payment |
| Bug fixes / support | 60 days free; optional support plan afterwards |
| Payment terms | 15% advance, then per milestone (Section 5) |
| Delivery time | Option 1: 6 weeks. Option 2: 9 weeks. Add-ons add the time shown in Section 6. |